## Case #1 Demo Dataset
Group | Axis Y | Details | Start Date | End Date | Description | Category | Type | Value | Sorting | Manager | Budget | Status
Marketing | Go mobile! | New mobile application | 2020-11-01 | 2021-02-28 | Better UX and upgraded functionality | Running | Phase | 0.6 | 7 | Bob Loiter | 10000 | 1
Marketing | Go mobile! | MockUp approval | 2020-12-15 | 2020-12-15 | By Marketing director | MinorCheck | Milestone | 0.5 | 8
Marketing | Go mobile! | GoLive | 2021-02-28 | 2021-02-28 | For whole network | Major | Milestone | 0.4 | 9
Marketing | E2E campaigns | Campaign management system | 2021-01-03 | 2021-06-30 | Planning, execution and evaluation of campaigns | Running | Phase | 0.2 | 10 | Megan Harley | 150000 | 2
Marketing | E2E campaigns | Pilot campaign | 2021-03-01 | 2021-03-01 | To be choosen | Minor | Milestone | 0.1 | 11
Marketing | E2E campaigns | Online channel RollOut | 2021-05-02 | 2021-05-02 | Online channel tryout | MinorCheck | Milestone | 0.2 | 12
Marketing | E2E campaigns | Steering committee approval | 2021-06-30 | 2021-06-30 | Solution accepted | Major | Milestone | 0.8 | 13
Sales | Network Boost | Sales network reorganisation | 2020-10-11 | 2021-01-07 | Revision of regional responsibilities | Finished | Phase | 1 | 1 | John Doe | 25000 | 3
Sales | Network Boost | Reorganization approved | 2020-12-19 | 2020-12-19 | By Sales director | Major | Milestone | 0.4 | 2
Sales | New tools | CRM implementation | 2020-11-28 | 2021-05-30 | Know your client - 360° view of client information | Running | Phase | 0.4 | 3 | Liz Treelaney | 180000 | 2
Sales | New tools | Vendor acquired | 2020-12-19 | 2020-12-19 | In public tender | Minor | Milestone | 0.2 | 4
Sales | New tools | Solution defined | 2021-01-28 | 2021-01-28 | All requirements specified | MinorCheck | Milestone | 0.6 | 5
Sales | New tools | Online channel pilot | 2021-04-04 | 2021-04-04 | Pilot + evaluation | Minor | Milestone | 0.7 | 6
Sales | New tools | XX | 2021-11-01 | 2021-04-30 | XX | Plan | InfoColumn | 0.7 | 6
Operations | Cost reduction | Invoicing process optimisation | 2020-10-17 | 2021-01-28 | Invoicing process cycle time reduction | Finished | Phase | 1 | 14 | Helen Dupree | 80000 | 1
Operations | Cost reduction | First phase inciated | 2020-11-12 | 2020-11-12 | Project scope defined | MinorCheck | Milestone | 0.1 | 15
Operations | Cost reduction | Final touch | 2021-01-12 | 2021-01-12 | Finetunning started | Major | Milestone | 0.5 | 16
Operations | Cost reduction | Hiring process optimisation | 2021-02-12 | 2021-05-30 | Responsibilities and simplified steps | Planned | Phase | 0.1 | 17 | Craig Coogan | 15000 | 2
Operations | Cost reduction | New workflow designed | 2021-04-07 | 2021-04-07 | Simplified worklow designed and discussed | MinorCheck | Milestone | 0.3 | 18
Operations | Meet regulations | Financial reporting standardisation | 2021-05-05 | 2021-08-31 | Implement standards across whole group | Planned | Phase | 0.05 | 19 | Kevin Weston | 28000 | 3
Operations | Meet regulations | Compliance check | 2021-07-14 | 2021-07-14 | Regulatory requirements met? | Minor | Milestone | 0.2 | 20

## Case #2 Demo Dataset
Continent | GroupOrder | Country | SubGroupOrder | ProductCategory | Product | Label | Start Date | End Date | Description | Category | Type
Europe | 1 | Italy | 3 | Product Category 1 | Product A | Assessment | 2023-04-30 | 2023-05-30 |  | 1. Assessment | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product A | APV | 2023-05-30 | 2023-05-30 |  | 1. Approved | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product A | Partner Selection | 2023-05-31 | 2023-07-15 |  | 2. Partner Selection | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product A | TND | 2023-06-15 | 2023-06-15 |  | 2. Tender | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product A | CNT | 2023-07-15 | 2023-07-15 |  | 3. Contract | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product A | Market Introduction | 2023-07-16 | 2023-09-14 |  | 3. Market Introduction | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product A | SAL | 2023-09-14 | 2023-09-14 |  | 4. Sales | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product A | Baseline | 2023-04-15 | 2023-08-30 |  | 4. Baseline/plan | Plan
Europe | 1 | Italy | 3 | Product Category 1 | Product A | Baseline | 2023-05-15 | 2023-08-15 | 🟠 | 4. Baseline/plan | InfoColumn
Europe | 1 | Italy | 3 | Product Category 1 | Product B | Assessment | 2023-05-23 | 2023-06-22 |  | 1. Assessment | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product B | APV | 2023-06-22 | 2023-06-22 |  | 1. Approved | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product B | Partner Selection | 2023-06-23 | 2023-08-07 |  | 2. Partner Selection | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product B | TND | 2023-07-08 | 2023-07-08 |  | 2. Tender | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product B | CNT | 2023-08-07 | 2023-08-07 |  | 3. Contract | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product B | Market Introduction | 2023-08-08 | 2023-10-07 |  | 3. Market Introduction | Phase
Europe | 1 | Italy | 3 | Product Category 1 | Product B | SAL | 2023-10-07 | 2023-10-07 |  | 4. Sales | Milestone
Europe | 1 | Italy | 3 | Product Category 1 | Product B | Baseline | 2023-05-03 | 2023-09-17 |  | 4. Baseline/plan | Plan
Europe | 1 | Italy | 3 | Product Category 1 | Product B | Baseline | 2023-06-02 | 2023-08-28 | 🔴 | 4. Baseline/plan | InfoColumn
Europe | 1 | Germany | 1 | Product Category 3 | Product E | Assessment | 2023-04-10 | 2023-05-10 |  | 1. Assessment | Phase
Europe | 1 | Germany | 1 | Product Category 3 | Product E | APV | 2023-05-10 | 2023-05-10 |  | 1. Approved | Milestone
Europe | 1 | Germany | 1 | Product Category 3 | Product E | Partner Selection | 2023-05-11 | 2023-06-25 |  | 2. Partner Selection | Phase
Europe | 1 | Germany | 1 | Product Category 3 | Product E | TND | 2023-05-26 | 2023-05-26 |  | 2. Tender | Milestone
Europe | 1 | Germany | 1 | Product Category 3 | Product E | CNT | 2023-06-25 | 2023-06-25 |  | 3. Contract | Milestone
Europe | 1 | Germany | 1 | Product Category 3 | Product E | Market Introduction | 2023-06-26 | 2023-08-25 |  | 3. Market Introduction | Phase
Europe | 1 | Germany | 1 | Product Category 3 | Product E | SAL | 2023-08-25 | 2023-08-25 |  | 4. Sales | Milestone
Europe | 1 | Germany | 1 | Product Category 3 | Product E | Baseline | 2023-04-05 | 2023-08-20 |  | 4. Baseline/plan | Plan
Europe | 1 | Germany | 1 | Product Category 3 | Product E | Baseline | 2023-05-05 | 2023-08-15 | 🟠 | 4. Baseline/plan | InfoColumn
Europe | 1 | France | 2 | Product Category 1 | Product A | Assessment | 2023-04-15 | 2023-05-15 |  | 1. Assessment | Phase
Europe | 1 | France | 2 | Product Category 1 | Product A | APV | 2023-05-15 | 2023-05-15 |  | 1. Approved | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product A | Partner Selection | 2023-05-16 | 2023-06-30 |  | 2. Partner Selection | Phase
Europe | 1 | France | 2 | Product Category 1 | Product A | TND | 2023-05-31 | 2023-05-31 |  | 2. Tender | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product A | CNT | 2023-06-30 | 2023-06-30 |  | 3. Contract | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product A | Market Introduction | 2023-07-01 | 2023-08-30 |  | 3. Market Introduction | Phase
Europe | 1 | France | 2 | Product Category 1 | Product A | SAL | 2023-08-30 | 2023-08-30 |  | 4. Sales | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product A | Baseline | 2023-05-05 | 2023-09-19 |  | 4. Baseline/plan | Plan
Europe | 1 | France | 2 | Product Category 1 | Product A |  | 2023-06-04 | 2023-10-09 | 🟢 | 4. Baseline/plan | InfoColumn
Europe | 1 | France | 2 | Product Category 1 | Product B | Assessment | 2023-05-28 | 2023-06-27 |  | 1. Assessment | Phase
Europe | 1 | France | 2 | Product Category 1 | Product B | APV | 2023-06-27 | 2023-06-27 |  | 1. Approved | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product B | Partner Selection | 2023-06-28 | 2023-08-12 |  | 2. Partner Selection | Phase
Europe | 1 | France | 2 | Product Category 1 | Product B | TND | 2023-07-13 | 2023-07-13 |  | 2. Tender | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product B | CNT | 2023-08-12 | 2023-08-12 |  | 3. Contract | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product B | Market Introduction | 2023-08-13 | 2023-10-12 |  | 3. Market Introduction | Phase
Europe | 1 | France | 2 | Product Category 1 | Product B | SAL | 2023-10-12 | 2023-10-12 |  | 4. Sales | Milestone
Europe | 1 | France | 2 | Product Category 1 | Product B | Baseline | 2023-05-03 | 2023-09-17 |  | 4. Baseline/plan | Plan
Europe | 1 | France | 2 | Product Category 1 | Product B | Baseline | 2023-06-12 | 2023-09-02 | 🔴 | 4. Baseline/plan | InfoColumn
Europe | 1 | France | 2 | Product Category 2 | Product C | Assessment | 2023-08-01 | 2023-08-31 |  | 1. Assessment | Phase
Europe | 1 | France | 2 | Product Category 2 | Product C | APV | 2023-08-31 | 2023-08-31 |  | 1. Approved | Milestone
Europe | 1 | France | 2 | Product Category 2 | Product C | Partner Selection | 2023-09-01 | 2023-10-16 |  | 2. Partner Selection | Phase
Europe | 1 | France | 2 | Product Category 2 | Product C | TND | 2023-09-16 | 2023-09-16 |  | 2. Tender | Milestone
Europe | 1 | France | 2 | Product Category 2 | Product C | CNT | 2023-10-16 | 2023-10-16 |  | 3. Contract | Milestone
Europe | 1 | France | 2 | Product Category 2 | Product C | Market Introduction | 2023-10-17 | 2023-12-16 |  | 3. Market Introduction | Phase
Europe | 1 | France | 2 | Product Category 2 | Product C | SAL | 2023-12-16 | 2023-12-16 |  | 4. Sales | Milestone
Europe | 1 | France | 2 | Product Category 2 | Product C | Baseline | 2023-07-27 | 2023-12-11 |  | 4. Baseline/plan | Plan
Europe | 1 | France | 2 | Product Category 2 | Product C | Baseline | 2023-08-26 | 2023-12-06 | 🟠 | 4. Baseline/plan | InfoColumn
Americas | 2 | USA | 1 | Product Category 1 | Product A | Assessment | 2023-05-28 | 2023-06-27 |  | 1. Assessment | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product A | APV | 2023-06-27 | 2023-06-27 |  | 1. Approved | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product A | Partner Selection | 2023-06-28 | 2023-08-12 |  | 2. Partner Selection | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product A | TND | 2023-07-13 | 2023-07-13 |  | 2. Tender | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product A | CNT | 2023-08-12 | 2023-08-12 |  | 3. Contract | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product A | Market Introduction | 2023-08-13 | 2023-10-12 |  | 3. Market Introduction | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product A | SAL | 2023-10-12 | 2023-10-12 |  | 4. Sales | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product A | Baseline | 2023-06-09 | 2023-10-24 |  | 4. Baseline/plan | Plan
Americas | 2 | USA | 1 | Product Category 1 | Product A |  | 2023-07-09 | 2023-11-05 | 🟢 | 4. Baseline/plan | InfoColumn
Americas | 2 | USA | 1 | Product Category 1 | Product B | Assessment | 2023-07-05 | 2023-08-04 |  | 1. Assessment | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product B | APV | 2023-08-04 | 2023-08-04 |  | 1. Approved | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product B | Partner Selection | 2023-08-05 | 2023-09-19 |  | 2. Partner Selection | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product B | TND | 2023-08-20 | 2023-08-20 |  | 2. Tender | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product B | CNT | 2023-09-19 | 2023-09-19 |  | 3. Contract | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product B | Market Introduction | 2023-09-20 | 2023-11-19 |  | 3. Market Introduction | Phase
Americas | 2 | USA | 1 | Product Category 1 | Product B | SAL | 2023-11-19 | 2023-11-19 |  | 4. Sales | Milestone
Americas | 2 | USA | 1 | Product Category 1 | Product B | Baseline | 2023-07-23 | 2023-12-07 |  | 4. Baseline/plan | Plan
Americas | 2 | USA | 1 | Product Category 1 | Product B |  | 2023-07-24 | 2023-11-26 | 🟢 | 4. Baseline/plan | InfoColumn
Americas | 2 | USA | 1 | Product Category 2 | Product D | Assessment | 2023-11-05 | 2023-12-05 |  | 1. Assessment | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product D | APV | 2023-12-05 | 2023-12-05 |  | 1. Approved | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product D | Partner Selection | 2023-12-06 | 2024-01-20 |  | 2. Partner Selection | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product D | TND | 2023-12-21 | 2023-12-21 |  | 2. Tender | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product D | CNT | 2024-01-20 | 2024-01-20 |  | 3. Contract | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product D | Market Introduction | 2024-01-21 | 2024-03-21 |  | 3. Market Introduction | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product D | SAL | 2024-03-21 | 2024-03-21 |  | 4. Sales | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product D | Baseline | 2023-11-14 | 2024-03-30 |  | 4. Baseline/plan | Plan
Americas | 2 | USA | 1 | Product Category 2 | Product D |  | 2023-12-14 | 2024-04-08 | 🟢 | 4. Baseline/plan | InfoColumn
Americas | 2 | USA | 1 | Product Category 2 | Product C | Assessment | 2023-11-30 | 2023-12-30 |  | 1. Assessment | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product C | APV | 2023-12-30 | 2023-12-30 |  | 1. Approved | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product C | Partner Selection | 2023-12-31 | 2024-02-14 |  | 2. Partner Selection | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product C | TND | 2024-01-15 | 2024-01-15 |  | 2. Tender | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product C | CNT | 2024-02-14 | 2024-02-14 |  | 3. Contract | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product C | Market Introduction | 2024-02-15 | 2024-04-15 |  | 3. Market Introduction | Phase
Americas | 2 | USA | 1 | Product Category 2 | Product C | SAL | 2024-04-15 | 2024-04-15 |  | 4. Sales | Milestone
Americas | 2 | USA | 1 | Product Category 2 | Product C | Baseline | 2023-10-21 | 2024-03-06 |  | 4. Baseline/plan | Plan
Americas | 2 | USA | 1 | Product Category 2 | Product C |  | 2023-10-22 | 2023-12-28 | 🔴 | 4. Baseline/plan | InfoColumn
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | Assessment | 2023-05-15 | 2023-06-14 |  | 1. Assessment | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | APV | 2023-06-14 | 2023-06-14 |  | 1. Approved | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | Partner Selection | 2023-06-15 | 2023-07-30 |  | 2. Partner Selection | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | TND | 2023-06-30 | 2023-06-30 |  | 2. Tender | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | CNT | 2023-07-30 | 2023-07-30 |  | 3. Contract | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | Market Introduction | 2023-07-31 | 2023-09-29 |  | 3. Market Introduction | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | SAL | 2023-09-29 | 2023-09-29 |  | 4. Sales | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product A | Baseline | 2023-05-25 | 2023-10-09 |  | 4. Baseline/plan | Plan
Americas | 2 | Mexico | 2 | Product Category 1 | Product A |  | 2023-07-04 | 2023-10-29 | 🟢 | 4. Baseline/plan | InfoColumn
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | Assessment | 2023-07-30 | 2023-08-29 |  | 1. Assessment | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | APV | 2023-08-29 | 2023-08-29 |  | 1. Approved | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | Partner Selection | 2023-08-30 | 2023-10-14 |  | 2. Partner Selection | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | TND | 2023-09-14 | 2023-09-14 |  | 2. Tender | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | CNT | 2023-10-14 | 2023-10-14 |  | 3. Contract | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | Market Introduction | 2023-10-15 | 2023-12-14 |  | 3. Market Introduction | Phase
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | SAL | 2023-12-14 | 2023-12-14 |  | 4. Sales | Milestone
Americas | 2 | Mexico | 2 | Product Category 1 | Product B | Baseline | 2023-07-05 | 2023-11-19 |  | 4. Baseline/plan | Plan
Americas | 2 | Mexico | 2 | Product Category 1 | Product B |  | 2023-09-18 | 2023-12-09 | 🔴 | 4. Baseline/plan | InfoColumn
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | Assessment | 2023-09-30 | 2023-10-30 |  | 1. Assessment | Phase
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | APV | 2023-10-30 | 2023-10-30 |  | 1. Approved | Milestone
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | Partner Selection | 2023-10-31 | 2023-12-15 |  | 2. Partner Selection | Phase
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | TND | 2023-11-15 | 2023-11-15 |  | 2. Tender | Milestone
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | CNT | 2023-12-15 | 2023-12-15 |  | 3. Contract | Milestone
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | Market Introduction | 2023-12-16 | 2024-02-14 |  | 3. Market Introduction | Phase
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | SAL | 2024-02-14 | 2024-02-14 |  | 4. Sales | Milestone
Americas | 2 | Mexico | 2 | Product Category 2 | Product C | Baseline | 2023-09-25 | 2024-02-09 |  | 4. Baseline/plan | Plan
Americas | 2 | Mexico | 2 | Product Category 2 | Product C |  | 2023-11-19 | 2024-02-29 | 🟠 | 4. Baseline/plan | InfoColumn
Asia | 3 | China | 2 | Product Category 2 | Product C | Assessment | 2023-05-28 | 2023-06-27 |  | 1. Assessment | Phase
Asia | 3 | China | 2 | Product Category 2 | Product C | APV | 2023-06-27 | 2023-06-27 |  | 1. Approved | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product C | Partner Selection | 2023-06-28 | 2023-08-12 |  | 2. Partner Selection | Phase
Asia | 3 | China | 2 | Product Category 2 | Product C | TND | 2023-07-13 | 2023-07-13 |  | 2. Tender | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product C | CNT | 2023-08-12 | 2023-08-12 |  | 3. Contract | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product C | Market Introduction | 2023-08-13 | 2023-10-12 |  | 3. Market Introduction | Phase
Asia | 3 | China | 2 | Product Category 2 | Product C | SAL | 2023-10-12 | 2023-10-12 |  | 4. Sales | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product C | Baseline | 2023-05-16 | 2023-09-30 |  | 4. Baseline/plan | Plan
Asia | 3 | China | 2 | Product Category 2 | Product C | Baseline | 2023-06-15 | 2023-09-18 | 🟠 | 4. Baseline/plan | InfoColumn
Asia | 3 | China | 2 | Product Category 2 | Product D | Assessment | 2023-07-05 | 2023-08-04 |  | 1. Assessment | Phase
Asia | 3 | China | 2 | Product Category 2 | Product D | APV | 2023-08-04 | 2023-08-04 |  | 1. Approved | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product D | Partner Selection | 2023-08-05 | 2023-09-19 |  | 2. Partner Selection | Phase
Asia | 3 | China | 2 | Product Category 2 | Product D | TND | 2023-08-20 | 2023-08-20 |  | 2. Tender | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product D | CNT | 2023-09-19 | 2023-09-19 |  | 3. Contract | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product D | Market Introduction | 2023-09-20 | 2023-11-19 |  | 3. Market Introduction | Phase
Asia | 3 | China | 2 | Product Category 2 | Product D | SAL | 2023-11-19 | 2023-11-19 |  | 4. Sales | Milestone
Asia | 3 | China | 2 | Product Category 2 | Product D | Baseline | 2023-07-23 | 2023-12-07 |  | 4. Baseline/plan | Plan
Asia | 3 | China | 2 | Product Category 2 | Product D | Baseline | 2023-07-24 | 2023-11-26 | 🟢 | 4. Baseline/plan | InfoColumn
Asia | 3 | China | 2 | Product Category 3 | Product F | Assessment | 2023-11-20 | 2023-12-20 |  | 1. Assessment | Phase
Asia | 3 | China | 2 | Product Category 3 | Product F | APV | 2023-12-20 | 2023-12-20 |  | 1. Approved | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product F | Partner Selection | 2023-12-21 | 2024-02-04 |  | 2. Partner Selection | Phase
Asia | 3 | China | 2 | Product Category 3 | Product F | TND | 2024-01-05 | 2024-01-05 |  | 2. Tender | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product F | CNT | 2024-02-04 | 2024-02-04 |  | 3. Contract | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product F | Market Introduction | 2024-02-05 | 2024-04-05 |  | 3. Market Introduction | Phase
Asia | 3 | China | 2 | Product Category 3 | Product F | SAL | 2024-04-05 | 2024-04-05 |  | 4. Sales | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product F | Baseline | 2023-12-02 | 2024-04-17 |  | 4. Baseline/plan | Plan
Asia | 3 | China | 2 | Product Category 3 | Product F | Baseline | 2023-12-08 | 2024-04-05 | 🟢 | 4. Baseline/plan | InfoColumn
Asia | 3 | China | 2 | Product Category 3 | Product E | Assessment | 2023-10-15 | 2023-11-14 |  | 1. Assessment | Phase
Asia | 3 | China | 2 | Product Category 3 | Product E | APV | 2023-11-14 | 2023-11-14 |  | 1. Approved | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product E | Partner Selection | 2023-11-15 | 2023-12-30 |  | 2. Partner Selection | Phase
Asia | 3 | China | 2 | Product Category 3 | Product E | TND | 2023-11-30 | 2023-11-30 |  | 2. Tender | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product E | CNT | 2023-12-30 | 2023-12-30 |  | 3. Contract | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product E | Market Introduction | 2023-12-31 | 2024-02-29 |  | 3. Market Introduction | Phase
Asia | 3 | China | 2 | Product Category 3 | Product E | SAL | 2024-02-29 | 2024-02-29 |  | 4. Sales | Milestone
Asia | 3 | China | 2 | Product Category 3 | Product E | Baseline | 2023-08-26 | 2024-01-10 |  | 4. Baseline/plan | Plan
Asia | 3 | China | 2 | Product Category 3 | Product E | Baseline | 2023-09-06 | 2023-11-02 | 🔴 | 4. Baseline/plan | InfoColumn
Asia | 3 | Japan | 1 | Product Category 1 | Product A | Assessment | 2023-04-30 | 2023-05-30 |  | 1. Assessment | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product A | APV | 2023-05-30 | 2023-05-30 |  | 1. Approved | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product A | Partner Selection | 2023-05-31 | 2023-07-15 |  | 2. Partner Selection | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product A | TND | 2023-06-15 | 2023-06-15 |  | 2. Tender | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product A | CNT | 2023-07-15 | 2023-07-15 |  | 3. Contract | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product A | Market Introduction | 2023-07-16 | 2023-09-14 |  | 3. Market Introduction | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product A | SAL | 2023-09-14 | 2023-09-14 |  | 4. Sales | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product A | Baseline | 2023-05-05 | 2023-09-19 |  | 4. Baseline/plan | Plan
Asia | 3 | Japan | 1 | Product Category 1 | Product A | Baseline | 2023-06-04 | 2023-09-24 | 🟢 | 4. Baseline/plan | InfoColumn
Asia | 3 | Japan | 1 | Product Category 1 | Product B | Assessment | 2023-05-23 | 2023-06-22 |  | 1. Assessment | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product B | APV | 2023-06-22 | 2023-06-22 |  | 1. Approved | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product B | Partner Selection | 2023-06-23 | 2023-08-07 |  | 2. Partner Selection | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product B | TND | 2023-07-08 | 2023-07-08 |  | 2. Tender | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product B | CNT | 2023-08-07 | 2023-08-07 |  | 3. Contract | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product B | Market Introduction | 2023-08-08 | 2023-10-07 |  | 3. Market Introduction | Phase
Asia | 3 | Japan | 1 | Product Category 1 | Product B | SAL | 2023-10-07 | 2023-10-07 |  | 4. Sales | Milestone
Asia | 3 | Japan | 1 | Product Category 1 | Product B | Baseline | 2023-06-01 | 2023-10-16 |  | 4. Baseline/plan | Plan
Asia | 3 | Japan | 1 | Product Category 1 | Product B | Baseline | 2023-06-27 | 2023-10-21 | 🟢 | 4. Baseline/plan | InfoColumn
Asia | 3 | Japan | 1 |  | Product Pilot | Assessment | 2023-06-29 | 2023-07-29 |  | 1. Assessment | Phase
Asia | 3 | Japan | 1 |  | Product Pilot | APV | 2023-07-29 | 2023-07-29 |  | 1. Approved | Milestone
Asia | 3 | Japan | 1 |  | Product Pilot | Partner Selection | 2023-07-30 | 2023-09-13 |  | 2. Partner Selection | Phase
Asia | 3 | Japan | 1 |  | Product Pilot | TND | 2023-08-14 | 2023-08-14 |  | 2. Tender | Milestone
Asia | 3 | Japan | 1 |  | Product Pilot | CNT | 2023-09-13 | 2023-09-13 |  | 3. Contract | Milestone
Asia | 3 | Japan | 1 |  | Product Pilot | Market Introduction | 2023-09-14 | 2023-11-13 |  | 3. Market Introduction | Phase
Asia | 3 | Japan | 1 |  | Product Pilot | SAL | 2023-11-13 | 2023-11-13 |  | 4. Sales | Milestone
Asia | 3 | Japan | 1 |  | Product Pilot | Baseline | 2023-07-04 | 2023-11-18 |  | 4. Baseline/plan | Plan
Asia | 3 | Japan | 1 |  | Product Pilot | Baseline | 2023-08-03 | 2023-11-23 | 🟢 | 4. Baseline/plan | InfoColumn
[7 empty] | 2023-07-01 | 2023-08-15 | ProductionOff | TargetInterval1 | Target
[7 empty] | 2024-07-01 | 2024-08-15 | ProductionOff | TargetInterval1 | Target

## Case #3 Demo Dataset (Hours)
Hotel | Activity | Place | Details | Start Date | End Date | Shift | Category | Type | Sorting
London | Reception | Main Reception | John + Frida | 2023-01-09 | 2023-01-09 08:00 | Shift 1 | Main Reception | Phase | 11
London | Reception | Main Reception | Maya + Linda + Jonathan | 2023-01-09 08:00 | 2023-01-09 16:00 | Shift 2 | Main Reception | Phase | 11
London | Reception | Main Reception | Lincoln + Florence + Clarence | 2023-01-09 16:00 | 2023-01-10 | Shift 3 | Main Reception | Phase | 11
London | Reception | Front Door Service | Melvin | 2023-01-09 06:00 | 2023-01-09 18:00 | Shift 1 | Front Door Service | Phase | 12
London | Reception | Front Door Service | Tobias | 2023-01-09 16:00 | 2023-01-09 22:00 | Shift 2 | Front Door Service | Phase | 12
London | Reception | Lobby/Elevators | Chloe | 2023-01-09 14:00 | 2023-01-09 20:00 | Shift 1 | Lobby/Elevators | Phase | 13
London | Restaurant | Restaurant | Theresa + Pierre | 2023-01-09 07:00 | 2023-01-09 13:00 | Shift 1 | Restaurant | Phase | 21
London | Restaurant | Restaurant | Theresa + Pierre + Oliver | 2023-01-09 13:00 | 2023-01-09 22:00 | Shift 2 | Restaurant | Phase | 21
London | Restaurant | Bar | Eduadro the Bartender | 2023-01-09 18:00 | 2023-01-10 | Shift 1 | Bar | Phase | 22
London | Restaurant | Kitchen | Riccardo the SousChef | 2023-01-09 05:00 | 2023-01-09 13:00 | Shift 1 | Kitchen | Phase | 23
London | Restaurant | Kitchen | Pablo the Chef | 2023-01-09 12:00 | 2023-01-09 22:00 | Shift 2 | Kitchen | Phase | 23
London | Cleaning | Room Service | Marry + Lorna + Peter | 2023-01-09 10:00 | 2023-01-09 16:00 | Shift 1 | Room Service | Phase | 31
London | Cleaning | Laundry | Leona | 2023-01-09 03:00 | 2023-01-09 09:00 | Shift 1 | Laundry | Phase | 32
London | Other | Management | Sonny | 2023-01-09 08:00 | 2023-01-09 18:00 | Shift 1 | Management | Phase | 41
London | Other | Maintanance | Johnny | 2023-01-09 07:00 | 2023-01-09 14:00 | Shift 1 | Maintanance | Phase | 42

## Case #4 Demo Dataset
Release | Topics | Order | Label | Start Date | End Date | Description | Category | Type
Release 1 | Sprints | Row1 | Planning | 2023-09-01 | 2023-09-01 |  | 1. Planning | Milestone
Release 1 | Sprints | Row1 | Review | 2023-09-26 | 2023-09-26 |  | 2. Review | Milestone
Release 1 | Sprints | Row1 | Retrospective | 2023-09-29 | 2023-09-29 |  | 3. Retrospective | Milestone
Release 1 | Sprints | Row1 | Delivery | 2023-09-01 | 2023-09-25 |  | 4. Sprint phases | Phase
Release 1 | Sprints | Row1 | Stakeholder review | 2023-09-26 | 2023-09-28 |  | 4. Sprint phases | Phase
Release 1 | Sprints | Row1 | WrapUp | 2023-09-29 | 2023-09-30 |  | 4. Sprint phases | Phase
Release 1 | Features | Row2 | Feature1 | 2023-09-04 | 2023-09-13 |  | 1. High | Phase
Release 1 | Features | Row3 | Feature2 | 2023-09-07 | 2023-09-25 |  | 1. High | Phase
Release 1 | Features | Row2 | Feature3 | 2023-10-05 | 2023-10-25 |  | 1. High | Phase
Release 1 | Features | Row3 | Feature4 | 2023-10-10 | 2023-10-25 |  | 2. Medium | Phase
Release 1 | UX | Row4 | Different Web viewers suport | 2023-09-04 | 2023-09-20 |  | 1. High | Phase
Release 1 | UX | Row4 | Mobile view optimisation | 2023-10-04 | 2023-10-24 |  | 1. High | Phase
Release 1 | UX | Row5 | New icon set implementation | 2023-09-12 | 2023-09-22 |  | 2. Medium | Phase
Release 1 | UX | Row5 | User feedback implementations | 2023-10-10 | 2023-10-25 |  | 2. Medium | Phase
Release 1 | UX | Row6 | Color scheme optimisation | 2023-10-20 | 2023-10-25 |  | 3. Low | Phase
Release 1 | Integrations | Row7 | Major payment gates integrations | 2023-09-08 | 2023-09-25 |  | 1. High | Phase
Release 1 | Integrations | Row7 | Third party SW integration | 2023-10-09 | 2023-10-26 |  | 2. Medium | Phase
Release 1 | Integrations | Row8 | Audit SW integration | 2023-09-15 | 2023-09-25 |  | 3. Low | Phase
Release 1 | Sprints | Row1 | Planning | 2023-10-02 | 2023-10-02 |  | 1. Planning | Milestone
Release 1 | Sprints | Row1 | Review | 2023-10-26 | 2023-10-26 |  | 2. Review | Milestone
Release 1 | Sprints | Row1 | Retrospective | 2023-10-30 | 2023-10-30 |  | 3. Retrospective | Milestone
Release 1 | Sprints | Row1 | Delivery | 2023-10-02 | 2023-10-25 |  | 4. Sprint phases | Phase
Release 1 | Sprints | Row1 | Stakeholder review | 2023-10-26 | 2023-10-28 |  | 4. Sprint phases | Phase
Release 1 | Sprints | Row1 | WrapUp | 2023-10-29 | 2023-10-31 |  | 4. Sprint phases | Phase
|  |  |  | 2023-09-01 | 2023-09-30 | Sprint 1 | Sprint1 | Target
|  |  |  | 2023-10-01 | 2023-10-31 | Sprint 2 | Sprint2 | Target
Formulas:
End Date = [Start Date]